AI for Good Robotics Competition

Match Timing & Schedule Analysis

2026 Grand Finale

────────────────────────────────────────────────────────────────────────────────

ROLE OF THE SCORING APPLICATION

The scoring application has no involvement in managing or enforcing the physical match clock. The two-minute match timer and the one-minute break between matches are handled entirely on the competition floor by referees and event staff. The app's role begins only after a match ends.

What the App Does

- Referee opens the scoring panel immediately after the match and records the breakdown.

- Scores save to the live scoreboard in real time — visible to spectators instantly.

- The admin can assign a scheduled start time to each match, which is displayed in the spectator Schedule view and on the MC's match cards.

- Status chips (Upcoming / Live / Done) update automatically based on scoring activity.

What the App Does Not Do

- It does not run a match countdown or enforce the 2-minute limit.

- It does not automatically advance phases based on the clock.

- It does not alert referees when a match should start.

Timing responsibility: Referees watch the physical match, track the 2-minute window, then immediately enter scores in the app. The app records outcomes — it does not manage time.

TEAM COUNT — 2026 GRAND FINALE

| CATEGORY | TEAMS | MATCHES PER QUALIFYING ROUND |
| --- | --- | --- |
| Junior | 32 | 16 |
| Senior | 37 | 18 |
| Total | 69 | 34 |

QUALIFYING ROUNDS — 90 MINUTES ALLOCATED PER ROUND

With 4 qualifying rounds, 69 teams generate 136 total qualifier matches (64 Junior + 72 Senior). The table below shows estimated time per round based on the number of simultaneous fields and a realistic cycle time of 5 minutes per match (2 min match + 1 min break + ~2 min for team arrival, field reset, and scoring).

| FIELDS PER CATEGORY | JUNIOR (16 MATCHES) | SENIOR (18 MATCHES) | ASSESSMENT |
| --- | --- | --- | --- |
| 1 field | 80 min | 90 min | Tight for Senior |
| 2 fields | 40 min | 45 min | ✅ Comfortable |
| 3 fields | 30 min | 30 min | ✅ Fast |
| 4 fields | 20 min | 25 min | ✅ Very Fast |

Assumptions

Junior and Senior categories run simultaneously on separate fields.

Cycle time: 5 minutes per match (2 min match + 1 min mandated break + ~2 min logistics).

Teams are paired for each round and the schedule is prepared in advance.

ELIMINATION ROUNDS — 60 MINUTES ALLOCATED (+ 30 MIN POSSIBLE EXTENSION)

Assuming the top 8 teams from each category advance into the elimination bracket, the following matches are required across both categories combined:

| PHASE | MATCHES PER CATEGORY | COMBINED (BOTH CATEGORIES) |
| --- | --- | --- |
| Quarterfinals | 4 | 8 |
| Semifinals | 2 | 4 |
| Third Place | 1 | 2 |
| Finals | 1 | 2 |
| Total | 8 | 16 |

Time Required

| FIELDS AVAILABLE | TIME (5 MIN/MATCH) | FITS IN 60 MIN? | FITS IN 90 MIN? |
| --- | --- | --- | --- |
| 1 shared field | 80 min | ❌ No | ✅ Yes |
| 2 simultaneous fields | 40 min | ✅ Yes | ✅ Yes |

Recommendation: Use the full 30-minute extension (budget 90 minutes total for elimination). Even with 2 fields, finals ceremonies, potential score reviews, and crowd management typically add 15–30 minutes beyond the calculated match time. The extra buffer eliminates scheduling pressure during the most important matches of the day.

SUMMARY & RECOMMENDATIONS

| ITEM | ALLOCATED | ASSESSMENT | RECOMMENDATION |
| --- | --- | --- | --- |
| Qualifying round (× 4) | 90 min each | Sufficient with 2+ fields | 2 fields per category recommended |
| Elimination rounds total | 60 min | Tight on 1 field; fine on 2 | Use the 30-min extension → 90 min total |
| Match timing enforcement | — | Not handled by app | Use physical timers on the floor |
| Schedule display in app | Supported | Admin sets times; MC + spectators see them | Enter schedule before event day |

AI for Good Robotics Competition — Internal Planning Document — 2026 Grand Finale